## PROJECT
COMMUNICATIONS MANAGEMENT PLAN
PROJECT DETAILS
PROJECT No: | WR 001
DATE: | 2026-02-01
PROJECT NAME: | SmilePoint Dental Clinic – Online Appointment Booking Portal
PROJECT MANAGER: | Jane Doe
PROJECT SPONSOR: | Clinic Owner

## COMMUNICATIONS MANAGEMENT PLAN
COMMUNICATIONS MANAGEMENT PLAN
ID | STAKEHOLDER NAME | INFORMATION | MODE OF COMMUNICATION | TIMING OR FREQUENCY | owner ROLE
SH1 | Clicnic owner(project sponsor) | PROJECT UPDATES, risks, budget | EMAIL | WEEKLY REPORTS | PM
SH2 | Clinic Manager | progress, issues | meeting | daily reports | BA
SH3 | Receptionist | traning | workshop | bi-weekly | BA
SH4 | Denists | Schedule impact, training schedule, feedback sessions | Email + In-clinic workshops + Demo sessions | Bi-weekly during design/testing | Business Analyst
SH5 | Patients | New portal benefits, how-to guides, launch announcement | Clinic posters, SMS blasts, Website/Facebook, Email newsletter | Pre-launch (2 weeks before) + Ongoing | Marketing Team
SH6 | Busines analyst | All feedback, approvals | Internal project meetings | As needed | Project Manager
SH7 | IT vendor (developer) | Detailed requirements, design specs, change requests, testing feedback, deployment schedule, support SLAs | Jira/Trello tickets + Daily/weekly stand-ups + Email + Video calls | Daily stand-ups (during dev) + Weekly progress + As-needed | Project Manager (PM)
SH8 | Compliance | Compliance reports (data privacy, security, consent), audit trails, risk mitigation for patient data | Formal email reports + Official submissions | As required (pre-go-live + periodic audits) | Clinic Manager / Legal Contact